## Task List
# | Section | Task | Priority | Suggested Owner | Assigned To | Status | Notes | Source
1 | Data ingestion health — blocking before POC kicks off next week | Root-cause the AWS integration going Unhealthy when the S3 metrics option is enabled | High | Elastic |  | Not Started |  | Corbett, 9/3
2 | Data ingestion health — blocking before POC kicks off next week | Confirm the AWS agentless-ingest bug fix clears QA (India team) and ships to prod | High | Elastic |  | Not Started |  | Tim Webster, 9/2
3 | Data ingestion health — blocking before POC kicks off next week | Stand up the fallback EC2 Elastic Agent for AWS collection while the agentless fix is pending | High | GE Vernova |  | Not Started |  | guide shared 9/2
4 | Data ingestion health — blocking before POC kicks off next week | Hold 48 hours of stable AWS integration data before the POC formally kicks off (~week of 9/8) | High | Joint |  | Not Started |  | Corbett, 9/1
5 | Data ingestion health — blocking before POC kicks off next week | Monitor agentless ingest stability now that it's reportedly fixed | Med | Elastic |  | Not Started |  | Brad, 9/3
6 | Data ingestion health — blocking before POC kicks off next week | Investigate why Infrastructure Inventory shows RDS but not EC2 or S3 buckets | High | GE Vernova/Elastic |  | Not Started |  | Corbett, 8/31
7 | Data ingestion health — blocking before POC kicks off next week | Confirm existing Observability serverless project's ES/Kibana covers AWS Billing integration (no separate instance needed) | Med | Elastic |  | Not Started |  | Corbett, 8/28
8 | Data ingestion health — blocking before POC kicks off next week | Confirm the IAM trust-policy / malformed-principal issue (account 291803666758) is fully resolved | Low | GE Vernova |  | Not Started |  | Corbett, 8/28
9 | OTel / Kubernetes telemetry | Complete kubeletstats + RBAC + k8s_observer config across all 3 clusters (pss-usw02-stage-ueks, smartsignal-usw02-stage-ueks, apm-stage) | High | GE Vernova |  | Not Started |  | Brad's guide, 9/3
10 | OTel / Kubernetes telemetry | Validate CPU/memory/network/disk metrics appear once kubeletstats config lands | High | Elastic |  | Not Started |  | shoeb couldn't find them, 9/3
11 | OTel / Kubernetes telemetry | Chase down missing traces — metrics are flowing but no traces confirmed yet | High | Elastic/GE Vernova |  | Not Started |  | Kate, 9/2
12 | OTel / Kubernetes telemetry | Confirm OTel SDKs point at the collector OTLP endpoint for trace emission | Med | GE Vernova |  | Not Started |  | Brad, 9/2
13 | OTel / Kubernetes telemetry | Clean up legacy service.telemetry.resource config warning in collector logs | Low | GE Vernova |  | Not Started |  | collector logs, 9/2
14 | Log ingestion (ESF / Lambda) | Fill in real region/account/SQS queue values in config.yaml for WAF, ELB, Fargate, EKS logs (currently placeholders) | High | GE Vernova |  | Not Started |  | config.yaml, working folder
15 | Log ingestion (ESF / Lambda) | Stand up per-data-source SQS queues (buffering, replay, batching) per Kate's ESF guidance | Med | GE Vernova |  | Not Started |  | Kate, 8/28
16 | Log ingestion (ESF / Lambda) | Confirm the datastream reroute from logs-esf.cloudwatch-default to logs-kubernetes.container_logs-default is fully applied | Med | GE Vernova |  | Not Started |  | shoeb, 9/2–9/3
17 | Log ingestion (ESF / Lambda) | Validate EKS control-plane audit logs route correctly rather than staying CloudWatch-wrapped JSON | Low | Elastic |  | Not Started |  | config.yaml note
18 | Program, access & enablement | Confirm Ajit Kamath has working Slack/channel access | Med | Elastic |  | Not Started |  | Udit, 8/26
19 | Program, access & enablement | Schedule/deliver the cloud & LLM usage cost-tracking demo to Udit's team | Med | Elastic |  | Not Started |  | Kate, 8/26
20 | Program, access & enablement | Confirm the daily 9:30am CST engineering sync is running smoothly | Low | Joint |  | Not Started |  | Udit, 8/26
21 | Program, access & enablement | Nudge the GE Vernova team to complete the two Instruqt workshops (Search 9.4, ES¦QL) | Low | GE Vernova |  | Not Started |  | Corbett, 8/12
22 | Splunk O11y → Elastic migration scoping (business case) | Re-run o11y_inventory.py with --include-charts to get chart names + reuse data | High | Elastic |  | Not Started |  | olly_inventory_summary.md §2
23 | Splunk O11y → Elastic migration scoping (business case) | Extend the inventory pull against Splunk's alert-events + audit-log APIs for real usage history | Med | Elastic |  | Not Started |  | summary §9
24 | Splunk O11y → Elastic migration scoping (business case) | Build the 5 Wave-1 priority dashboards (RDS Prod, MQ Prod, Cache Instance, K8s container, EC2 instances) — ~79% of alert traffic | High | Elastic |  | Not Started |  | summary §7
25 | Splunk O11y → Elastic migration scoping (business case) | Scope/build the remaining 92 Wave-1 dashboards via AWS + Kubernetes OOTB integrations | Med | Elastic |  | Not Started |  | summary §7
26 | Splunk O11y → Elastic migration scoping (business case) | Budget custom dashboard build for AmazonMQ + ElastiCache — no OOTB Elastic dashboard, 978 alert refs (most underestimated piece) | High | Elastic |  | Not Started |  | summary Tier B
27 | Splunk O11y → Elastic migration scoping (business case) | Confirm with owners whether Tier C bespoke dashboards (CONFIG-SERVICE, Smart Factory Cloud, Security Service) are still in live use before committing rebuild effort | Med | Elastic/GE Vernova |  | Not Started |  | summary Tier C
28 | Splunk O11y → Elastic migration scoping (business case) | Consolidate the 8 SmartSignal RTE Memory dashboards into one dashboard with a site filter | Low | Elastic |  | Not Started |  | summary Tier C
29 | Splunk O11y → Elastic migration scoping (business case) | Confirm with SRE team which side (QA vs Prod) is authoritative for the 9 drifted detector pairs before consolidating | Med | GE Vernova |  | Not Started |  | summary §3
30 | Splunk O11y → Elastic migration scoping (business case) | Audit the 101 permanent (no-expiry) alert mutes — still needed or clean up? | Low | GE Vernova |  | Not Started |  | summary §3
31 | Splunk O11y → Elastic migration scoping (business case) | Investigate the 81 detectors with no notification configured — intentional or a gap? | Med | GE Vernova |  | Not Started |  | summary §3
32 | Splunk O11y → Elastic migration scoping (business case) | Confirm ServiceNow alert routing is part of the day-one Elastic design (78% of all notifications) | High | Elastic |  | Not Started |  | summary §8
33 | Splunk O11y → Elastic migration scoping (business case) | Ask SRE team about unsaved/interactive ad-hoc query volume and whether Discover/Lens need to be part of enablement | Low | Elastic |  | Not Started |  | summary §6b

## Summary
Section | Total | Not Started | In Progress | Blocked | Done | % Done
Data ingestion health — blocking before POC kicks off next week | 8 | 8 | 0 | 0 | 0 | 0%
OTel / Kubernetes telemetry | 5 | 5 | 0 | 0 | 0 | 0%
Log ingestion (ESF / Lambda) | 4 | 4 | 0 | 0 | 0 | 0%
Program, access & enablement | 4 | 4 | 0 | 0 | 0 | 0%
Splunk O11y → Elastic migration scoping (business case) | 12 | 12 | 0 | 0 | 0 | 0%
Total | 33 | 33 | 0 | 0 | 0 | 0%

## Legend
How to use this tracker
Task List tab: one row per open item, pulled from the #ext-elastic-ge-vernova / #ge-vernova-poc Slack channels and the migration-scoping files in the GEVernova_Observability working folder (as of Sept 4, 2026).
Columns to edit:
• Assigned To — enter the person's name (e.g. Kate Lawrence-Gupta, Corbett Merrill).
• Status — pick from the dropdown: Not Started, In Progress, Blocked, Done.
• Notes — free text for updates, blockers, or links.
Columns not meant to be edited (context from the research):
• Section, Task, Priority, Suggested Owner, Source.
• Suggested Owner is the team that appears responsible based on Slack context (Elastic / GE Vernova / Joint) — use Assigned To for a specific person.
Summary tab: auto-calculated counts and % complete per section via COUNTIFS formulas — updates automatically as you change Status.
Example row (for format reference only — not a real task):
# | Section | Task | Priority | Suggested Owner | Assigned To | Status | Notes | Source
0 | Example section | Example task description goes here | Med | Elastic | Jane Doe | In Progress | Waiting on customer to confirm access | Slack, 9/1